## Updated Project Timeline
HealthConnect Clinic AI Project – Updated Project Timeline (Week 5)
Updated to reflect the transition from Week 4 project initiation to Week 5 execution and progress monitoring.
Project Phase | Key Activity | Original Timing | Updated Timing | Current Status | Progress | Week 5 Update / Notes
Project Initiation | Review project documentation and Week 4 deliverables | Week 4 | Week 4–5 | Completed | 100% | Week 4 project documentation reviewed before execution activities began.
Project Planning | Convert major activities into actionable tasks | Week 5 | Week 5 | In Progress | 80% | Major activities translated into actionable tasks for the project workstreams.
Project Planning | Assign responsibilities across workstreams | Week 5 | Week 5 | In Progress | 70% | Initial responsibilities identified across Project Management, Data Analysis, Machine Learning and Generative AI.
Execution & Monitoring | Establish and maintain project task tracker | Week 5 | Week 5 | In Progress | 80% | Trello board created to track tasks, priorities, workstreams and progress status.
Execution & Monitoring | Conduct initial Data Analysis activities | Week 5 | Week 5–6 | In Progress | 30% | Initial dataset and Data Dictionary review tasks identified and scheduled.
Execution & Monitoring | Define Machine Learning problem and data requirements | Week 5 | Week 5–6 | Not Started | 0% | Dependent on initial data understanding and quality assessment.
Execution & Monitoring | Review Knowledge Base and identify patient enquiry categories | Week 5 | Week 5–6 | Not Started | 0% | Generative AI activities remain within the approved Knowledge Base scope.
Monitoring & Control | Update project timeline and monitor progress | Week 5 | Week 5–Ongoing | In Progress | 60% | Timeline updated to reflect current execution status and upcoming activities.
Monitoring & Control | Monitor risks and dependencies | Week 4–Ongoing | Week 5–Ongoing | In Progress | 50% | Existing risks and dependencies are being reviewed; emerging issues will be documented.
Monitoring & Control | Conduct cross-workstream progress review | Week 5 | Week 5–Ongoing | In Progress | 40% | Coordination approach established to monitor progress across technical workstreams.
Solution Development | Develop and test track-specific AI/data solutions | Future Phase | Weeks 6–7 | Not Started | 0% | Dependent on outputs from initial exploration and requirements definition.
Project Integration | Integrate workstream outputs and prepare final recommendations | Future Phase | Weeks 7–8 | Not Started | 0% | Dependent on completion of Data Analysis, ML and Generative AI activities.