## Risk & Dependency Register
ID | Type | Risk / Dependency | Description | Likelihood | Impact | Priority | Mitigation / Management Action | Owner | Status
R-01 | Risk | Data quality issues | Missing, inconsistent, or incomplete appointment data may affect analysis and later modelling. | Medium | High | High | Conduct an initial data quality assessment and document limitations before further analysis. | Data Analysis | Open / Monitoring
R-02 | Risk | Cross-workstream dependency delays | Delays in one technical workstream may affect downstream activities. | Medium | High | High | Track dependencies regularly and escalate blockers early. | Project Manager | Monitoring
R-03 | Risk | Scope creep | Additional requirements outside the approved scope may increase workload and affect the timeline. | Low | Medium | Medium | Check significant changes against the approved Scope Statement before acceptance. | Project Manager | Monitoring
R-04 | Risk | Knowledge Base scope limitations | The approved Knowledge Base may not contain sufficient information for every patient enquiry. | Medium | Medium | Medium | Keep Generative AI responses within the approved Knowledge Base and document content gaps. | Generative AI | Open
R-05 | Risk | Unclear task ownership | Unclear responsibilities may lead to duplicated work or missed tasks. | Low | High | Medium | Maintain task ownership and workstream labels in the Trello task tracker. | Project Manager | Mitigating
R-06 | Risk | Timeline slippage | Delays in early execution activities may affect later project phases. | Medium | High | High | Review progress regularly and update the project timeline when significant changes occur. | Project Manager | Monitoring
D-01 | Dependency | Data Analysis → Machine Learning | Machine Learning activities depend on initial data understanding and quality assessment. | High | High | High | Track completion of dataset review and communicate relevant outputs to the ML workstream. | Project Manager / Data Analysis | Active
D-02 | Dependency | Approved Knowledge Base → Generative AI | Generative AI work must remain within the information contained in the approved Knowledge Base. | High | High | High | Confirm Knowledge Base availability and scope before GenAI activities. | Generative AI | Active
D-03 | Dependency | Task Tracker → Progress Monitoring | Accurate status reporting depends on tasks being maintained in the tracker. | Medium | Medium | Medium | Review and update Trello task statuses regularly. | Project Manager | Active
D-04 | Dependency | Workstream Updates → Timeline | Timeline accuracy depends on current progress information from workstreams. | Medium | High | High | Use regular progress reviews to update status and timing. | Project Manager / Workstream Leads | Active
D-05 | Dependency | Risk Monitoring → Issue Management | Emerging issues need to be identified early for appropriate response. | Medium | Medium | Medium | Review risks during progress monitoring and document newly emerging issues. | Project Manager | Active
Week 5 Updated Risk & Dependency Register

## Notes
Week 5 Register Notes | Purpose / Guidance
Purpose | Update the Week 4 risk and dependency register to reflect the move into execution and progress monitoring.
Risk | An uncertain event or condition that could affect scope, schedule, quality, resources, or delivery.
Dependency | A condition, resource, decision, or output that another activity relies on to proceed.
Use in Week 5 | Review status regularly, add emerging risks, update mitigation actions, and use the register alongside the Trello task tracker.