## PM Record
HealthConnect Week 8 — Updated Project Timeline
Activity | Owner | Status | Dependency | Evidence / Output | Next Action
Week 8 transition review | PM | Completed | Week 7 outputs | Week 7 PM package + Week 8 assignment | Maintain transition summary
Collect final track updates | PM | In progress | All tracks | Data Analytics update received | Obtain remaining confirmations
Confirm Data Analytics final output | PM + Analytics | Ready | Analytics evidence | Analytical engine + dashboard + decision support | Carry into integration
Confirm Data Science final output | PM + DS | Pending confirmation | Final model/probabilities | No Week 8 confirmation received | Request status/evidence
Confirm ML Engineering final output | PM + ML | Pending confirmation | Final API/integration | No Week 8 confirmation received | Request status/evidence
Confirm GenAI final output | PM + GenAI | Pending confirmation | Final assistant/demo | No Week 8 confirmation received | Request status/evidence
Resolve cross-track dependencies | PM + relevant tracks | In progress | DS probabilities; ML/API; scheduling parameters | Dependency register | Coordinate owners/evidence
Final integration walkthrough | All tracks + PM | Upcoming | Track outputs confirmed | Final integration record | Schedule walkthrough
Presentation coordination | PM + all tracks | Upcoming | Final sections | Presentation plan | Assign sequence/roles
Final readiness assessment | PM | Pending | Final confirmations | Readiness assessment | Update after integration
Project closure | PM | Upcoming | Readiness confirmed | Closure summary | Complete final submission