## PM Record
HealthConnect Week 8 — Final Workstream Status
Track | Final Output | Status | Week 7→8 Result | Dependency | Evidence | Presentation Role
Data Analytics | Python analytical engine; executive dashboard; decision support package | READY | 106 null records handled; 50 ratio anomalies capped; 4-panel dashboard; TS-01–TS-05 reported PASS | ML/API alignment; DS probability weights; scheduling parameters | GitHub/artifacts reported | Analytics; hygiene; friction insights; decision support
Data Science | Final model / probability output | PENDING CONFIRMATION | Not received by PM | Final probabilities and model metrics | Pending | Pending
ML Engineering | Final integrated ML workflow | PENDING CONFIRMATION | Not received by PM | API/integration confirmation | Pending | Pending
GenAI | Final assistant and demonstration | PENDING CONFIRMATION | Not received by PM | Final assistant/demo evidence | Pending | Pending
Project Management | Final integration, readiness and presentation coordination | IN PROGRESS | Coordinating final status/dependencies/walkthrough | Track confirmations | PM records | Integration; readiness; presentation