## PM Record
HealthConnect Week 8 — Outstanding Issues / Dependency Register
ID | Source | Issue / Dependency | Impact | Status | Owner | Next Step
DEP-01 | Analytics | API endpoint alignment with ML Engineering for live scheduling/scoring | High | Open | ML + Analytics + PM | Confirm interface requirements
DEP-02 | Analytics → DS | Final production model probability weights for threshold synchronization (<0.30 as stated by Analytics) | High | Open | DS + Analytics + PM | Confirm final probabilities/threshold
DEP-03 | Analytics → Operations | Scheduling database parameters for WhatsApp trigger mapping | Medium/High | Open | Operations + Analytics + PM | Confirm parameters
DEP-04 | PM | Data Science Week 8 confirmation/evidence not received | High | Open | PM + DS | Request final update
DEP-05 | PM | ML Engineering Week 8 confirmation/evidence not received | High | Open | PM + ML | Request final update
DEP-06 | PM | GenAI Week 8 confirmation/evidence not received | Medium/High | Open | PM + GenAI | Request final update
DEP-07 | Analytics | Real-world WhatsApp conversion remains uncertain | Medium | Limitation | Analytics + PM | Document; do not present as validated
DEP-08 | Analytics | Teleconsultation requires operational/technical validation | Medium | Limitation | Analytics + Operations + PM | Document validation requirement