## PM Record
HealthConnect Week 8 — Final Risk Register
ID | Risk | Impact | Control | Status | Owner | Final Integration Action
R-01 | Final cross-track outputs not fully confirmed | High | PM tracking | Open | PM | Confirm all required outputs
R-02 | Analytics/ML API alignment not confirmed | High | Dependency tracked | Open | ML + Analytics | Confirm technical interface
R-03 | Final DS probabilities/threshold pending | High | Dependency tracked | Open | DS + Analytics | Confirm model output
R-04 | WhatsApp trigger parameters pending | Medium/High | Dependency tracked | Open | Operations + Analytics | Confirm database parameters
R-05 | Real-world WhatsApp conversion uncertain | Medium | Working assumption documented | Limitation | Analytics + PM | Do not overstate validation
R-06 | Teleconsultation recommendation needs real-world validation | Medium | Limitation documented | Limitation | Analytics + Operations | Document requirement
R-07 | Final GenAI evidence not received | Medium/High | PM tracking | Open | GenAI + PM | Confirm status/evidence