## PM Record
HealthConnect Week 8 — Final Decision Log
ID | Decision | Basis | Status | Owner
DEC-01 | Use actual track confirmations as final status | PM will not assume unreported completion | Active | PM
DEC-02 | Record Data Analytics as READY | Analytics explicitly reported READY and supplied output/dependency details | Active | PM + Analytics
DEC-03 | Keep DS, ML and GenAI pending until final updates are received | No final Week 8 confirmation/evidence received by PM | Active | PM
DEC-04 | Treat Analytics–ML API alignment as final integration dependency | Explicitly identified by Analytics | Open | ML + Analytics + PM
DEC-05 | Treat final DS probability outputs as final integration dependency | Explicitly requested by Analytics | Open | DS + Analytics + PM
DEC-06 | Treat WhatsApp conversion and teleconsultation as limitations/validation requirements | Analytics report states real-world validation is still required | Active | Analytics + PM