## Updated Timeline
HealthConnect Week 7 — Updated Project Timeline
Activity | Owner | Planned Stage | Actual Status | Dependency | Evidence / Output | Week 8 Carry-Forward
Collect team testing evidence | Project Management | Week 7 | Completed | Team submissions | Screenshots + written testing evidence | —
Consolidate Testing Activity Tracker | Project Management | Week 7 | Completed | All submitted test results | Testing Activity Tracker | Update if new evidence arrives
Update Integration & Issue Log | Project Management | Week 7 | Completed / Open items retained | Testing findings | Issue Log | Close remaining issues
Update Risk / Dependency Register | Project Management | Week 7 | Completed | Open risks and dependencies | Risk/Dependency Register | Monitor R-02, R-03, R-05, R-06, R-07
Record Week 7 decisions | Project Management | Week 7 | Completed | Testing outcomes | Decision Log | Update if final integration changes decisions
Cross-track coordination documentation | Project Management + tracks | Week 7 | Completed for submitted evidence | Analytics↔DS; ML↔Analytics; DS handoff | Cross-Track Record | Continue end-to-end validation
Testing Progress / Status Report | Project Management | Week 7 | Completed | Tracker + issue/risk records | Status Report | Update with final Week 7 closure
Week 8 readiness assessment | Project Management | Week 7 | Partially Ready | Outstanding dependencies | Readiness Assessment | Resolve/accept outstanding items
Final probability outputs for Power BI | Data Science / PM coordination | Week 8 | Pending | Final model outputs | Outstanding Action | Required for risk filtering
Operational threshold validation | Data Science / PM coordination | Week 8 | Pending | Use-case validation | Risk Register / Outstanding Action | Validate before treating threshold as final
Corrected handoff adoption confirmation | Data Science / PM coordination | Week 8 | Pending | Corrected handoff with distance_missing | Outstanding Action | Confirm adopted version
ML logging discrepancy follow-up | ML Engineering | Week 8 | Pending | Logging review | Issue Log | Resolve or document
Final end-to-end integration | All tracks / PM coordination | Week 8 | Upcoming | Closure of key dependencies | Week 8 integration package | Final validation and presentation