## Testing Tracker
HealthConnect Week 7 — Testing Activity Tracker
Test ID | Track / Collaboration | Component / Activity | Expected / Test Scope | Actual Result | Status | Issue / Finding | Action / Refinement | Retest / Validation | Evidence
TS-01 | Data Analytics | Baseline KPI reconciliation | Total 1,000; attended 728 (72.8%); no-show 272 (27.2%) | Total 1,000; attended 728 (72.8%); no-show 272 (27.2%) | PASS | No discrepancy; baseline integrity verified | No discrepancy; baseline integrity verified |  | Dashboard evidence
TS-02 | Data Analytics | Reminder channel imputation audit | 106 null entries categorized as None; 29.25% default rate | 106 null entries categorized as None; 29.25% default rate | PASS | Explicit None category | Explicit None category | Retest PASS; 100% filter stability | Analytics dashboard / written evidence
TS-03 | Data Analytics | Ratio anomaly cap test | 50 records had raw ratios up to 1.500; expected maximum 1.000 | 50 records had raw ratios up to 1.500; expected maximum 1.000 | FAIL → PASS | previous_no_shows exceeded previous_appointments; applied .clip(upper=1.0) | previous_no_shows exceeded previous_appointments; applied .clip(upper=1.0) | Retest PASS; max ratio 1.000 | Written test evidence
TS-04 | Data Analytics | Departmental slicer cross-filtering | Pediatrics: 255 total; 30.59% no-show | Pediatrics: 255 total; 30.59% no-show | PASS | No issue; DAX/Excel dynamic filter context verified | No issue; DAX/Excel dynamic filter context verified | Retest PASS | Analytics dashboard
TS-05 | Data Analytics | High-friction interaction validation | Flag 0: 27.15%; Flag 1: 30.77% | Flag 0: 27.15%; Flag 1: 30.77% | PASS | Interaction metric promoted to executive dashboard card | Interaction metric promoted to executive dashboard card | Retest PASS | Analytics dashboard
ML-01–ML-10 | ML Engineering | Integrated pipeline reliability | Valid input, required fields, invalid numerics, unseen categories, feature engineering, preprocessing, batch prediction, reload, threshold, reproducibility | Valid input, required fields, invalid numerics, unseen categories, feature engineering, preprocessing, batch prediction, reload, threshold, reproducibility | PASS | Refined custom transformer, normalized reminder values, numeric validation and logging | Refined custom transformer, normalized reminder values, numeric validation and logging | 10/10 core tests passed | ML testing summary screenshot
REF-01–REF-03 | ML Engineering | Refinement and regression tests | Input validation refinement; invalid-input retest; valid-input regression | Input validation refinement; invalid-input retest; valid-input regression | PASS | Refinements applied | Refinements applied | 13/13 total tests passed; 100% | ML testing screenshots
DA-DS-01 | Data Analytics ↔ Data Science | DAX precision + feature matrix ingestion | Initial DAX 60.00% vs expected 61.76%; ingestion ValueError on missing reminder values | Initial DAX 60.00% vs expected 61.76%; ingestion ValueError on missing reminder values | FAIL → PASS | Excluded Cancelled; imputed reminder_channel as No Reminder; re-exported CSV | Excluded Cancelled; imputed reminder_channel as No Reminder; re-exported CSV | 61.76% exact across slicers; 5,000 records ingested with zero execution errors | Written evidence / dashboard
DS-01 | Data Science handoff | Handoff data-quality validation | 0 duplicate IDs; 0 risk-score/tier mismatches; 86 missing distance values (1.8%) | 0 duplicate IDs; 0 risk-score/tier mismatches; 86 missing distance values (1.8%) | PARTIAL FAIL → PASS | Added distance_missing indicator; corrected handoff re-exported | Added distance_missing indicator; corrected handoff re-exported | Core modelling columns had zero nulls; corrected file 10 columns vs original 9 | Written evidence