## Issue Log
HealthConnect Week 7 — Integration & Issue Log
ISS-01 | Data Analytics | previous_no_shows exceeded previous_appointments; raw ratios up to 1.500 | Data quality / KPI integrity | Applied .clip(upper=1.0) | Closed | Data Analytics | Monitor in final data refresh
ISS-02 | Data Analytics / ML | Missing/unexpected reminder values caused handling issues | Preprocessing / filter stability | Explicit None / No Reminder handling and normalization | Closed | Analytics + ML | Confirm final encoded version
ISS-03 | Data Analytics ↔ DS | Cancelled appointments included in DAX denominator | KPI accuracy | Explicit appointment_outcome <> Cancelled filter | Closed | Analytics + DS | Carry validated DAX into final dashboard
ISS-04 | Data Analytics | Static dashboard colour bindings caused overlap | Dashboard readability | Refinement recorded in analytics testing | Closed | Data Analytics | Confirm final visual state
ISS-05 | ML Engineering | Logging showed flagged-count discrepancy | Monitoring reliability | Follow-up required | Open | ML Engineering | Resolve or document before final integration
ISS-06 | ML / DS / PM | Configurable risk threshold not operationally validated | Decision/use-case risk | Track as dependency | Open | DS + PM | Validate threshold
ISS-07 | Data Science handoff | Corrected handoff adoption not yet confirmed | Integration consistency | Corrected file includes distance_missing | Open | DS + PM | Confirm adopted version
ISS-08 | Data Analytics | Reminder-timing data unavailable | Limits reminder analysis | Document limitation | Open | Analytics + PM | Obtain data or formally close limitation
ISS-09 | Data Science | 0–7 days × 3+ prior no-shows interaction has n=13 | Low-confidence finding | Do not over-interpret | Open | DS + PM | Review during final validation
ISS-10 | Data Science / Power BI | Final predicted probability outputs pending | Blocks risk filtering integration | Carry as Week 8 dependency | Open | DS + PM | Provide final probabilities