## Risk Dependency Register
HealthConnect Week 7 — Updated Risk / Dependency Register
ID | Risk / Dependency | Impact | Likelihood | Current Control / Mitigation | Status | Owner | Week 8 Action
R-01 | Moderate predictive performance | Medium/High | Medium | Retain evaluation metrics; validate threshold operationally | Open | Data Science + PM | Validate operational use
R-02 | Risk threshold not operationally validated | High | Medium | Do not treat threshold as final until validated | Open | Data Science + PM | Threshold validation
R-03 | ML flagged-count logging discrepancy | Medium | Medium | Follow-up logging review | Open | ML Engineering | Resolve or document
R-04 | Distance missingness in handoff | Medium | Medium | distance_missing indicator added | Controlled | Data Science | Confirm corrected handoff adoption
R-05 | Reminder timing data unavailable | Medium | Medium | Limitation documented | Open | Data Analytics + PM | Obtain data or formally document limitation
R-06 | Low-confidence n=13 interaction | Medium | Medium | Avoid over-interpretation | Open | Data Science | Review in final validation
R-07 | Final predicted probability outputs pending | High | High | Tracked as Week 8 integration dependency | Open | Data Science + PM | Provide final probabilities for Power BI