## Decision Log
HealthConnect Week 7 — Decision Log
Decision ID | Date / Stage | Decision | Reason / Evidence | Owner | Status
DEC-01 | Week 7 | Record only submitted testing evidence as completed | PM evidence control; do not assume completion without evidence | Project Management | Active
DEC-02 | Week 7 | Use Test → Finding → Action → Retest → Validated Improvement | Matches assignment testing evidence structure | Project Management | Active
DEC-03 | Week 7→8 | Use corrected DS handoff with distance_missing, subject to adoption confirmation | 86 distance values were missing; corrected file makes missingness explicit | DS + PM | Pending confirmation
DEC-04 | Week 7→8 | Carry unresolved issues into Week 8 | Open dependencies must remain visible rather than marked resolved without evidence | Project Management | Active
DEC-05 | Week 7→8 | Treat final predicted probabilities as a Week 8 dependency | Required for Power BI risk filtering | DS + PM | Pending
DEC-06 | Week 7→8 | Do not treat configurable threshold as operationally final until validated | Technical test pass does not establish operational suitability | DS + PM | Pending validation