## High-Level Timeline
HEALTHCONNECT CLINIC – HIGH-LEVEL PROJECT TIMELINE
Project Management Track ¦ High-Level Planning Timeline
Timeline Assumption | The timeline is a high-level planning view based on project phases and dependencies. Exact calendar dates can be adjusted to match the official internship/project schedule.
Phase ID | Project Phase / Activity | Key Activities | Duration | Start Week | Finish Week | Key Dependency | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
1.0 | Project Initiation & Understanding | Review business scenario, objectives, requirements, resources, and define Project Management contribution. | 1 week | Week 4 | Week 4 | Project resources available | ●
2.0 | Project Planning | Develop Charter, Scope Statement, Stakeholder Register, WBS, Timeline, Risk & Dependency Register, and Communication Approach. | 1 week | Week 4 | Week 4 | Completion of project understanding | ●
3.0 | Data Analysis Workstream | Review data and Data Dictionary, assess quality, prepare data, conduct exploratory analysis, and document findings. | 2 weeks | Week 5 | Week 6 | Access to appointment data and Data Dictionary |  | ● | ●
4.0 | Machine Learning Workstream | Define prediction problem, prepare modelling data, explore model approaches, evaluate findings, and document results. | 2 weeks | Week 6 | Week 7 | Data preparation and relevant analysis outputs |  |  | ● | ●
5.0 | Generative AI Workstream | Review Knowledge Base, define AI scope, design response approach, validate scope compliance, and document findings. | 2 weeks | Week 5 | Week 6 | Access to approved Knowledge Base |  | ● | ●
6.0 | Integration & Coordination | Coordinate workstreams, monitor dependencies, review progress, and consolidate key findings. | 3 weeks | Week 5 | Week 7 | Workstream progress and outputs |  | ● | ● | ●
7.0 | Reporting & Close-out | Compile project outputs, review deliverables, consolidate findings, and document recommendations and next steps. | 1 week | Week 8 | Week 8 | Completion of key workstream outputs |  |  |  |  | ●
KEY PROJECT MILESTONES
Milestone ID | Milestone | Target Week | Success Indicator
M1 | Project Initiation Package Completed | Week 4 | All seven Project Management deliverables prepared.
M2 | Initial Data Exploration Completed | Week 6 | Key data quality observations and appointment patterns documented.
M3 | Machine Learning Exploration Completed | Week 7 | Initial model approach and evaluation findings documented.
M4 | Generative AI Exploration Completed | Week 6 | Knowledge Base scope and initial response approach documented.
M5 | Project Outputs Consolidated | Week 8 | Workstream findings and project documentation compiled.

## Timeline Notes
High-Level Timeline Notes
Purpose | This timeline provides a high-level sequence of the major HealthConnect project phases, workstreams, dependencies, and milestones.
Planning Basis | The sequence is aligned with the Work Breakdown Structure. Project Planning is completed first, while technical workstreams follow and are coordinated through Integration & Coordination.
Dependency Logic | Machine Learning activities depend on relevant data preparation and analysis outputs. Generative AI depends on access to the approved Knowledge Base. Final reporting depends on outputs from the relevant workstreams.
Flexibility | Week labels are used as planning assumptions because the assignment does not provide a detailed official calendar schedule. Dates can be updated when an official project schedule is available.