## Risk & Dependency Register
HEALTHCONNECT CLINIC – INITIAL RISK AND DEPENDENCY REGISTER
Project Management Track ¦ Week 4
ID | Type | Risk / Dependency | Description | Likelihood | Impact | Priority | Mitigation / Management Action | Owner
R-01 | Risk | Data Quality Issues | Missing, inconsistent, or incomplete appointment data may affect the reliability of analysis and subsequent modelling. | Medium | High | High | Conduct an initial data quality assessment and document identified limitations before further analysis. | Data Analysis Workstream
R-02 | Risk | Limited Project Time | The available project timeline may limit the depth of exploration and completion of planned activities. | High | Medium | High | Prioritise required deliverables, maintain a realistic timeline, and monitor progress against key milestones. | Project Manager
R-03 | Risk | Scope Creep | Additional requirements outside agreed project boundaries may increase workload and affect the project timeline. | Medium | High | High | Maintain the approved Scope Statement and document and assess significant change requests. | Project Manager
R-04 | Risk | Knowledge Base Scope Violation | A Generative AI solution may provide information outside the approved Knowledge Base or introduce invented clinic or medical information. | Medium | High | High | Define clear information boundaries and validate proposed AI responses against the approved Knowledge Base. | Generative AI Workstream
R-05 | Risk | Workstream Coordination Gaps | Poor coordination between workstreams may result in duplicated work, delays, or inconsistent outputs. | Medium | High | High | Use regular progress updates, defined responsibilities, and dependency tracking. | Project Manager
R-06 | Risk | Stakeholder Availability | Limited stakeholder availability may delay feedback, decisions, or clarification of requirements. | Medium | Medium | Medium | Plan communication early and escalate critical decisions when necessary. | Project Manager
R-07 | Risk | Resource Handling Errors | Original project resources could be accidentally altered or overwritten during analysis or processing. | Low | High | Medium | Preserve original resources and save cleaned, transformed, or processed data separately. | All Workstreams
R-08 | Risk | Unclear Requirements | Misinterpretation of the business problem or project requirements could lead to misaligned outputs. | Medium | High | High | Use the Project Charter, Scope Statement, and regular reviews to maintain alignment. | Project Manager
D-01 | Dependency | Appointment Dataset Availability | Data analysis and machine learning activities depend on access to the approved appointment dataset. | High | High | High | Confirm resource availability and maintain the original dataset separately from processed versions. | Data Analysis / ML Workstreams
D-02 | Dependency | Data Dictionary Availability | Accurate interpretation of dataset variables depends on access to the Data Dictionary. | High | High | High | Review the Data Dictionary before analysis and document assumptions about variables. | Data Analysis Workstream
D-03 | Dependency | Data Preparation Before Modelling | Machine learning exploration depends on relevant data cleaning and preparation activities. | High | High | High | Sequence the timeline so data preparation and initial analysis precede modelling activities. | Data Analysis / ML Workstreams
D-04 | Dependency | Knowledge Base Availability | Generative AI exploration depends on access to the approved HealthConnect Knowledge Base. | High | High | High | Confirm access and use the Knowledge Base as the defined information boundary. | Generative AI Workstream
D-05 | Dependency | Workstream Outputs | Integration and reporting depend on timely outputs from the Data Analysis, Machine Learning, and Generative AI workstreams. | Medium | High | High | Track milestones and dependencies through regular project coordination. | Project Manager / Workstream Leads
D-06 | Dependency | Stakeholder Input | Project decisions and validation may depend on stakeholder feedback and clarification. | Medium | Medium | Medium | Identify decision points early and communicate required inputs in advance. | Project Manager

## Register Notes
Risk & Dependency Register Notes
Purpose | This register captures the initial risks and dependencies that may affect the HealthConnect project. It supports early planning, monitoring, and coordination.
Risk Definition | A risk is an uncertain event or condition that could negatively affect project objectives, timeline, quality, or delivery.
Dependency Definition | A dependency is a condition, resource, decision, or output that must be available or completed for another activity to proceed successfully.
Priority Assessment | Priority is assessed qualitatively using the initial likelihood and impact ratings. The register should be reviewed and updated as the project progresses.