## Stakeholder Register
HEALTHCONNECT CLINIC – STAKEHOLDER REGISTER
Project Management Track ¦ Week 4
Stakeholder ID | Stakeholder | Role / Relationship | Interest in Project | Influence / Power | Key Expectations | Engagement Level | Communication Needs / Method | Project Manager Approach
SH-01 | HealthConnect Clinic Management | Primary business stakeholder and recipient of project outcomes. | High | High | Clear understanding of how data and AI can support appointment management and patient support. | Manage Closely | Project updates and key findings via meetings and summary reports. | Engage closely and seek feedback on project direction and business priorities.
SH-02 | Project Sponsor | Provides overall direction, support, and oversight for the project. | High | High | Project alignment with objectives, appropriate use of resources, and timely delivery of outputs. | Manage Closely | Milestone updates, risks, decisions, and progress summaries. | Provide regular status updates and escalate major risks or decisions when required.
SH-03 | Project Manager | Coordinates planning, stakeholders, workstreams, risks, dependencies, timeline, and communication. | High | High | Clear responsibilities, timely workstream updates, and coordinated project delivery. | Manage Closely | Regular coordination meetings, project documentation, and progress tracking. | Coordinate all stakeholder interactions and maintain project governance.
SH-04 | Data Analysis Workstream | Reviews and explores appointment data to identify relevant patterns and insights. | High | Medium | Clear requirements, access to approved data resources, and alignment with project objectives. | Keep Informed / Engage | Workstream meetings, task updates, and shared project documentation. | Maintain close coordination and track dependencies between analysis outputs and other workstreams.
SH-05 | Machine Learning Workstream | Explores machine learning approaches related to appointment no-show prediction or risk identification. | High | Medium | Clearly defined problem, suitable data inputs, and alignment with project requirements. | Keep Informed / Engage | Technical progress updates and coordination meetings. | Monitor progress and manage dependencies on data preparation and analysis outputs.
SH-06 | Generative AI Workstream | Explores AI-supported responses to repetitive patient enquiries within the approved Knowledge Base. | High | Medium | Clear scope boundaries and access to approved Knowledge Base content. | Keep Informed / Engage | Scope reviews, progress updates, and coordination meetings. | Ensure work remains within approved Knowledge Base boundaries and project scope.
SH-07 | Clinic Administrative Staff | Represents appointment-related administrative processes and operational support needs. | High | Medium | Improved support for appointment processes and reduced repetitive enquiries. | Keep Informed / Consult | Feedback sessions, interviews, or operational discussions. | Consult for practical insight into administrative processes and user needs.
SH-08 | Healthcare Providers | Indirectly affected by appointment attendance and scheduling efficiency. | Medium | Medium | Improved appointment utilisation and minimal disruption to operational processes. | Keep Informed | Relevant project updates and summary communications. | Keep informed of relevant findings and potential operational implications.
SH-09 | Patients | Primary beneficiaries of improved appointment engagement and patient support. | High | Low | Accessible support, clearer appointment information, and improved engagement. | Monitor / Consider Needs | Patient-focused requirements represented through business scenario and approved resources. | Ensure project decisions consider patient experience and remain within approved information boundaries.
SH-10 | IT / Data Support | Supports access, management, and appropriate handling of project data and technical resources where applicable. | Medium | Medium | Clear requirements for data access, resource handling, and technical coordination. | Keep Informed / Consult | Technical coordination and issue-based communication. | Engage when data access, storage, or technical dependencies arise.

## Register Notes
Stakeholder Register Notes
Purpose | This register identifies key stakeholders relevant to the HealthConnect project, their relationship to the project, level of interest and influence, expectations, communication needs, and the initial engagement approach.
Engagement Categories | Manage Closely: high interest/high influence stakeholders requiring active engagement. Keep Informed / Engage: stakeholders requiring regular updates and collaboration. Keep Informed / Consult: stakeholders whose operational input may be required. Monitor / Consider Needs: stakeholders with lower influence but important user needs.
Project Management Use | The register should be reviewed and updated as stakeholder roles, expectations, risks, or communication needs change during subsequent project phases.