## Coordination Record
HealthConnect — Week 6 Cross-Track Coordination Record
Project Management Track ¦ Coordination, exchanges, outcomes and evidence
Record ID | Date / Phase | Tracks Involved | Coordination Activity | Information / Output Exchanged | Purpose / Dependency | Outcome / Change | Evidence to Retain | Status
CTR-01 | Week 6 | Project Management + All Tracks | Week 6 asynchronous coordination through Slack | Track updates, deliverables, dependencies, needs/provisions and risks | Establish integration points and coordinate Week 6 activities | Responsibilities and integration points clarified; work continued asynchronously | Slack messages/screenshots; Trello timeline | Completed
CTR-02 | Week 6 | Data Analytics ↔ Data Science | Cross-track analytical/model comparison | Validated Analytics findings on lead time, appointment type, patient behaviour/segments and KPIs; Data Science error-analysis/model findings | Determine whether analytical patterns support or explain modelling observations | Integration activity underway; final comparison outcome should be documented when exchanged | Analytics output/handoff + Data Science analysis + Slack/file evidence | In progress
CTR-03 | Week 6 | Data Science → ML Engineering | Candidate model and requirements handoff | Improved candidate model, refined feature set and modelling requirements | Enable integration of improved model into reusable ML pipeline | Candidate model positioned for technical integration; ML pipeline integration was validated | Model artefact + pipeline documentation + validation evidence | Completed for current validation
CTR-04 | Week 6 | ML Engineering + Project Management | Pipeline integration status and validation review | Pipeline integration status, technical validation results and limitations | Support accurate PM status, issue/risk tracking and Week 7 readiness | 10/10 validation tests passed; ML Engineering activity moved to Completed on Trello | Validation/test evidence + Trello screenshot | Completed
CTR-05 | Week 6 | Project Management + Data Analytics | Analytics progress and operational implications review | Validated KPI progress, business-impact findings and operational recommendations | Support PM decisions, risk updates and HealthConnect objective alignment | Operational risk around uncontrolled overbooking was identified and mitigation recorded | Analytics findings + Updated Risk Register | Mitigated / monitor
CTR-06 | Week 6 | Project Management + GenAI | GenAI progress/evidence follow-up | GenAI evaluation, refinement, issues and dependencies | Complete PM coordination record and prepare Week 7 testing | Final GenAI status/evidence still needs confirmation | GenAI Week 6 output + Slack/file evidence | Pending confirmation
CTR-07 | Week 6 | Project Management + All Tracks | Week 7 testing coordination | Testing responsibilities, dependencies, required evidence and unresolved issues | Prepare transition from Week 6 integration/validation to Week 7 | Week 7 testing plan established across all tracks and end-to-end validation | Week 7 Testing Plan + Trello Week 7 list | Planned