## Decision Log
HealthConnect — Week 6 Decision Log
Project Management Track ¦ Major decisions and agreements recorded during Week 6
Decision ID | Decision / Agreement | Reason / Context | Owner | Tracks Affected | Evidence / Basis | Status
DEC-01 | Use the improved Data Science candidate model as the candidate for technical integration rather than simply repeating the Week 5 baseline. | Week 6 requires model improvement, comparison and validation before the next stage. | Data Science | Data Science; ML Engineering | Week 6 Data Science progress update and candidate-model readiness | Agreed / proceeding
DEC-02 | Use cross-track integration activities to compare Data Analytics findings with Data Science model/error-analysis findings. | The assignment requires meaningful integration and asks Analytics findings to support modelling decisions where relevant. | Project Management | Data Analytics; Data Science | Week 6 integration requirement; Analytics ↔ Data Science collaboration | In progress
DEC-03 | Move the ML Engineering pipeline integration/validation card to Completed after validation evidence showed 10/10 tests passed. | The activity has been validated for the current Week 6 stage and is ready for the next testing stage. | Project Management | ML Engineering | 10/10 validation tests passed; Trello status updated | Completed
DEC-04 | Use Trello as the project-level updated timeline and status view, with Excel registers providing detailed dependency, issue, risk and testing records. | Different artefacts serve different PM purposes and avoid duplicating detailed registers inside the timeline. | Project Management | All Tracks | Week 6 PM deliverable structure and current project workflow | Agreed / proceeding
DEC-05 | Do not treat every limitation as a blocker; record issues according to their actual effect on progress. | The current team updates identify limitations and risks, but not all prevent work from continuing. | Project Management | All Tracks | Team Week 6 updates and PM issue log | Agreed / proceeding
DEC-06 | Prepare Week 7 around testing, refinement and end-to-end validation rather than starting a new solution. | Week 6 progression is Improve → Integrate → Validate → Document → Prepare for Week 7; Week 7 moves into Testing → Refinement → End-to-End Validation. | Project Management | All Tracks | Week 6 assignment progression | Planned