## Integration Register
HealthConnect — Week 6 Integration & Dependency Register
Project Management Track ¦ Integration, Advanced Development & Validation
Tracks dependencies, integration readiness, status, PM action and evidence required for Week 7.
ID | Providing Track | Receiving Track | Dependency / Required Input | Why It Matters | Status | Current PM Action / Evidence | Evidence Type
ID-01 | Data Analytics | Data Science | Validated analytical findings, relevant patient/appointment patterns, KPI insights and feature-related findings | Supports modelling decisions and comparison with model/error-analysis results | Active — integration underway | Analytics ↔ Data Science collaboration; record the outcome | Analysis output / KPI evidence
ID-02 | Data Science | ML Engineering | Final candidate model, refined feature set and model requirements | Enables integration of the improved model into the reusable ML pipeline | Ready / integration path established | Candidate model identified; pipeline integration path established | Model artefact + integration evidence
ID-03 | ML Engineering | Data Science | Technical integration requirements, input/output expectations and pipeline compatibility feedback | Keeps model implementation compatible with the integrated pipeline | Monitor during integration | Document technical requirements and compatibility feedback | Pipeline documentation / validation
ID-04 | Data Analytics | Project Management | Validated KPIs, analytical progress, business-impact findings and operational recommendations | Supports project decisions, status tracking, risk/dependency updates and objective alignment | Active | Capture relevant analytical progress in PM records | Dashboard/report + PM record
ID-05 | GenAI | Project Management | Assistant progress, issues, dependencies and Week 6 evaluation/refinement status | Allows PM to track GenAI progress and unresolved dependencies | To confirm | Confirm final GenAI Week 6 integration information before marking complete | Assistant evaluation evidence
ID-06 | Project Management | All Tracks | Integration coordination, dependency tracking, risk/issue monitoring, timeline alignment and testing coordination | Keeps workstreams aligned and prepares the project for Week 7 testing | Active | PM coordination through Slack, Trello and project records | Trello + coordination record
ID-07 | Data Analytics | Data Science | Segment-level findings, lead-time patterns, patient behaviour insights and relevant analytical evidence | Helps compare observed patterns with model behaviour and error analysis | Active | Compare Analytics findings with Data Science error-analysis results | Analysis/handoff evidence
ID-08 | Data Science | ML Engineering | Improved modelling approach and validation results | Provides a validated candidate for technical pipeline integration rather than repeating the Week 5 baseline | Ready | Data Science reported improved candidate and readiness for integration | Model comparison + validation
ID-09 | ML Engineering | Project Management | Integration validation status, testing results, technical limitations and unresolved technical issues | Supports accurate status, issue/risk tracking and Week 7 readiness | Completed for current validation | 10/10 validation tests passed; pipeline moved to Completed on Trello | Testing/validation evidence
ID-10 | All Tracks | All Tracks | Relevant outputs, changes, limitations and validation evidence needed by dependent workstreams | Enables meaningful cross-track integration and end-to-end validation | Ongoing | Record actual integration outcomes and evidence; communication alone is not integration | Updated files / tests / artefacts

## Status Guide
Status Guide
Status | Meaning
Active | Dependency/integration is currently being worked on.
Ready | Required output is available or the integration can proceed.
To confirm | Information/evidence still needs confirmation; do not assume completion.
Completed | Relevant activity has been validated with available evidence.
Ongoing | Dependency remains relevant across the project and later testing.