## Issue Log
HealthConnect — Week 6 Integration Issue Log
Project Management Track ¦ Integration, Validation, Risks & Issue Monitoring
Records actual integration-related issues, observations, impacts, owners, mitigations and follow-up. Items are not treated as blockers unless they actually prevent progress.
Issue ID | Date / Phase | Track | Issue / Observation | Impact | Owner | Action / Mitigation | Status | Evidence / Follow-up
ISS-01 | Week 6 | Data Science | Model performance remains moderate; the improved candidate may still have limitations for operational use. | Prediction quality may affect the reliability of no-show risk classification and downstream decisions. | Data Science | Validate suitability for the intended use case and document limitations. Continue testing in Week 7. | Open — monitoring | Model comparison and validation results; Week 7 model testing
ISS-02 | Week 6 | Data Science / PM | A substantial share of test predictions falls in an uncertain probability range (0.4–0.6). | Uncertain cases may require careful thresholding or additional operational rules rather than automatic intervention. | Data Science + PM | Validate risk thresholds against intended interventions and document the limitation. | Open — monitoring | Error analysis / probability distribution; Week 7 threshold validation
ISS-03 | Week 6 | Data Analytics / PM | Applying risk scores without capacity controls could create overbooking congestion, particularly in Cardiology/GP. | Could reduce appointment-slot availability and create operational pressure. | Data Analytics + PM | Use a controlled overbooking approach with a maximum 12% buffer and no more than 2 additional slots per 4-hour clinical block. | Mitigated — monitor | Analytics recommendation; monitor during Week 7 validation
ISS-04 | Week 6 | Data Analytics | Some segmented or multi-variable groups may have small sample sizes. | Findings for small groups may be less reliable and should not be over-interpreted. | Data Analytics | Check appointment counts and document data limitations; distinguish association from causation. | Open — monitoring | Segment-level analysis and limitations
ISS-05 | Week 6 | ML Engineering | Prediction thresholds and the trade-off between false positives, false negatives and intervention capacity require validation. | An unsuitable threshold could create too many unnecessary interventions or miss high-risk appointments. | ML Engineering + PM | Confirm downstream business/operational requirements and test configurable thresholds during Week 7. | Open — monitoring | Pipeline threshold configuration; Week 7 testing
ISS-06 | Week 6 | ML Engineering | Future real-world generalisation and possible data drift remain limitations. | Performance may change when the solution is exposed to new data or operating conditions. | ML Engineering + Data Science | Document the limitation and include robustness/generalisation checks in later testing where applicable. | Open — monitoring | Technical documentation; future validation
ISS-07 | Week 6 | Cross-Track Integration | Final integration outcomes from GenAI still need to be confirmed for the PM record. | PM status and dependency documentation cannot be marked fully complete without the actual GenAI progress/evidence. | GenAI + PM | Obtain the Week 6 GenAI evaluation/refinement status and evidence; update the register. | Pending confirmation | GenAI Week 6 output / Slack coordination evidence
ISS-08 | Week 6 | Data Science / Data Analytics | Data Science requested comparison of model error patterns with Analytics findings, particularly around appointment type and patient behaviour. | Without comparison, it would be difficult to determine whether observed model errors reflect meaningful behavioural patterns. | Data Analytics + Data Science | Complete the Analytics ↔ Data Science comparison and document what changed or was confirmed. | In progress | Cross-track analysis / handoff evidence
ISS-09 | Week 6 | ML Engineering / Data Science | Technical input/output requirements need to remain aligned between the refined model and integrated pipeline. | Mismatch could cause integration or prediction-interface errors. | ML Engineering | Validate schema, preprocessing/model compatibility and pipeline interface; retain test evidence. | Resolved for current validation | 10/10 pipeline validation tests passed

## Status Guide
Issue Log Status Guide
Status | Meaning
Open — monitoring | Issue/limitation exists but does not currently prevent progress; continue monitoring and validate.
Mitigated — monitor | A mitigation has been defined/applied, but the condition should still be monitored.
Pending confirmation | Required information/evidence has not yet been confirmed.
In progress | Cross-track action is actively being worked on.
Resolved for current validation | The issue has been addressed for the current Week 6 validation stage; retain evidence.