## Risk Register
HealthConnect — Week 6 Updated Risk Register
Project Management Track ¦ Risks, limitations, mitigation and review points
Risk ID | Risk / Limitation | Track | Likelihood | Impact | Risk Level | Mitigation / Response | Owner | Status | Review Point
R-01 | Moderate predictive performance may limit reliability of no-show risk classification. | Data Science | Medium | High | High | Validate suitability for intended use, document limitations and continue model testing in Week 7. | Data Science + PM | Open — monitor | Week 7 model testing
R-02 | A sizeable share of test predictions falls in an uncertain probability range (0.4–0.6). | Data Science | Medium | Medium | Medium | Validate configurable thresholds against operational intervention needs; avoid treating uncertain predictions as definitive. | Data Science + PM | Open — monitor | Week 7 threshold validation
R-03 | Overbooking based on risk scores without capacity controls could create congestion in Cardiology/GP. | Data Analytics | Medium | High | High | Apply a maximum 12% overbooking buffer, capped at 2 additional slots per 4-hour clinical block; monitor operational impact. | Data Analytics + PM | Mitigated — monitor | Week 7 operational validation
R-04 | Small sample sizes in some segmented/multi-variable groups may reduce reliability of findings. | Data Analytics | Medium | Medium | Medium | Check appointment counts, document data limitations and distinguish association from causation. | Data Analytics | Open — monitor | Week 7 analytical testing
R-05 | Future real-world generalisation and possible data drift may affect model performance. | ML Engineering / Data Science | Medium | High | High | Document limitation and include robustness/generalisation checks where applicable in later validation. | ML Engineering + Data Science | Open — monitor | Week 7 / later validation
R-06 | Threshold trade-offs between false positives, false negatives and intervention capacity may affect operational usefulness. | ML Engineering | Medium | High | High | Confirm downstream business requirements and test configurable thresholds during Week 7. | ML Engineering + PM | Open — monitor | Week 7 testing
R-07 | GenAI Week 6 progress/evidence has not yet been fully confirmed for the PM record. | GenAI / PM | Medium | Medium | Medium | Obtain final GenAI evaluation/refinement status and update PM records before final submission. | GenAI + PM | Pending confirmation | Before Week 6 submission
R-08 | Cross-track comparison between Analytics findings and Data Science error patterns remains to be completed/documented. | Data Analytics / Data Science | Medium | Medium | Medium | Complete the Analytics ↔ Data Science comparison and capture the actual outcome/evidence. | Data Analytics + Data Science | In progress | Before Week 6 submission