## Week 7 Testing Plan
HealthConnect — Week 7 Testing Coordination Plan
Project Management Track ¦ Testing, refinement and end-to-end validation coordination
Test ID | Week 7 Area | Track / Owner | Testing Objective | Input / Dependency | Expected Evidence | Priority | Status | Coordination Note
T-01 | KPI & Dashboard Testing | Data Analytics | Validate refined KPIs, dashboard outputs and analytical recommendations against the Week 6 evidence. | Validated Week 6 analytics and updated dashboard/report | KPI validation results; dashboard evidence; documented findings | High | Planned | Confirm final Analytics output is available before testing.
T-02 | Model Testing & Validation | Data Science | Test the improved candidate model against defined evaluation criteria and assess suitability for HealthConnect. | Improved model, refined features, Week 6 evaluation results | Test metrics, error analysis, comparison and limitation notes | High | Planned | Include false-positive/false-negative and uncertain-probability analysis where applicable.
T-03 | ML Pipeline Testing | ML Engineering | Test integrated preprocessing, model interface, inputs/outputs and reproducibility under broader test conditions. | Integrated pipeline and model artefact | End-to-end pipeline test results; validation logs; issue evidence | High | Planned | Use the completed Week 6 integration as the baseline for broader testing.
T-04 | AI Assistant Testing | GenAI | Test assistant consistency, Knowledge Base adherence, unsupported requests and escalation behaviour. | Refined assistant, approved Knowledge Base and Week 6 test scenarios | Test cases/results; examples of improvements; limitations | High | Planned | Final Week 6 GenAI status should be confirmed before testing.
T-05 | Cross-Track End-to-End Validation | All Tracks / PM | Validate that integrated outputs work together and support the HealthConnect objective. | Analytics, Data Science, ML Engineering and GenAI outputs | End-to-end validation record; issues/decisions; final integration evidence | High | Planned | PM coordinates dependencies and records unresolved issues.
T-06 | Operational Threshold / Capacity Validation | PM + Data Analytics + ML Engineering | Assess whether risk thresholds and operational capacity controls are appropriate for intended use. | Risk scores, threshold options, capacity assumptions and Analytics recommendations | Threshold decision record; capacity-control evidence; risk update | Medium | Planned | Pay particular attention to overbooking constraints and intervention capacity.
T-07 | Integration Issue Retest | PM + relevant track | Retest issues carried from Week 6 after mitigation or refinement. | Week 6 Integration Issue Log and mitigation actions | Retest results and updated issue statuses | Medium | Planned | Only retest issues that remain relevant after Week 6.