## WBS
HEALTHCONNECT CLINIC – WORK BREAKDOWN STRUCTURE (WBS)
Project Management Track ¦ Week 4
WBS ID | Phase / Workstream | Activity / Work Package | Description | Primary Responsibility | Key Output
1.0 | Project Initiation & Understanding | Project Initiation & Understanding | Establish an initial understanding of the HealthConnect business problem, objectives, resources, and project context. | Project Manager | Shared understanding of project foundation
1.1 | Project Initiation & Understanding | Review Business Scenario | Review the HealthConnect business scenario, operational challenges, and central project question. | Project Manager | Business problem understanding
1.2 | Project Initiation & Understanding | Review Project Objective and Requirements | Review Week 4 objectives, track responsibilities, required outputs, and project instructions. | Project Manager | Requirements understanding
1.3 | Project Initiation & Understanding | Review Project Resources | Identify and review the appointment dataset, Data Dictionary, Knowledge Base, and approved project tools. | Project Manager / Workstreams | Resource understanding
1.4 | Project Initiation & Understanding | Define Project Management Contribution | Define the Project Management role and contribution to the broader HealthConnect initiative. | Project Manager | Track-specific role definition
2.0 | Project Planning | Project Planning | Develop the initial management framework required to guide and coordinate the project. | Project Manager | Project initiation package
2.1 | Project Planning | Develop Project Charter | Document project background, business problem, objectives, workstreams, assumptions, constraints, and initial approach. | Project Manager | Project Charter
2.2 | Project Planning | Develop Scope Statement | Define project boundaries, in-scope and out-of-scope activities, assumptions, constraints, and acceptance criteria. | Project Manager | Scope Statement
2.3 | Project Planning | Identify Stakeholders | Identify stakeholders relevant to the project and assess their roles, interest, influence, expectations, and engagement needs. | Project Manager | Stakeholder Register
2.4 | Project Planning | Develop Work Breakdown Structure | Break the broader project into structured phases, workstreams, and manageable activities. | Project Manager | Work Breakdown Structure
2.5 | Project Planning | Develop High-Level Timeline | Sequence major project phases and activities and identify key dependencies. | Project Manager | High-Level Timeline
2.6 | Project Planning | Identify Risks and Dependencies | Identify major risks, dependencies, potential impacts, and initial response actions. | Project Manager | Risk & Dependency Register
2.7 | Project Planning | Develop Communication Approach | Define stakeholder communication needs, methods, frequency, and responsibilities. | Project Manager | Communication Approach
3.0 | Data Analysis Workstream | Data Analysis Workstream | Explore appointment data to support understanding of patterns associated with appointment attendance and no-shows. | Data Analysis Team | Data insights
3.1 | Data Analysis Workstream | Review Dataset and Data Dictionary | Understand available variables, data definitions, and dataset structure. | Data Analysis Team | Data understanding
3.2 | Data Analysis Workstream | Data Quality Assessment | Identify missing values, inconsistencies, duplicates, or other data quality considerations. | Data Analysis Team | Data quality findings
3.3 | Data Analysis Workstream | Data Preparation | Clean or transform data as required while preserving the original project resources separately. | Data Analysis Team | Processed dataset
3.4 | Data Analysis Workstream | Exploratory Data Analysis | Explore appointment patterns and factors potentially associated with missed appointments. | Data Analysis Team | Initial analytical insights
3.5 | Data Analysis Workstream | Document Findings | Summarise key findings relevant to the HealthConnect business problem. | Data Analysis Team | Analysis summary
4.0 | Machine Learning Workstream | Machine Learning Workstream | Explore predictive approaches that may support identification or prediction of appointment no-show risks. | Machine Learning Team | ML exploration outputs
4.1 | Machine Learning Workstream | Define Prediction Problem | Define the machine learning problem in alignment with the HealthConnect business objective. | Machine Learning Team | Problem definition
4.2 | Machine Learning Workstream | Prepare Modelling Data | Prepare appropriate input data based on approved resources and prior data preparation outputs. | Machine Learning Team | Model-ready dataset
4.3 | Machine Learning Workstream | Explore Model Approach | Explore suitable modelling approaches for appointment no-show risk identification or prediction. | Machine Learning Team | Initial model approach
4.4 | Machine Learning Workstream | Evaluate Findings | Assess initial modelling results using appropriate evaluation considerations. | Machine Learning Team | Model evaluation findings
4.5 | Machine Learning Workstream | Document Results | Document modelling approach, findings, limitations, and observations. | Machine Learning Team | ML summary
5.0 | Generative AI Workstream | Generative AI Workstream | Explore how Generative AI can support responses to repetitive patient enquiries within approved information boundaries. | Generative AI Team | GenAI exploration outputs
5.1 | Generative AI Workstream | Review Knowledge Base | Review approved Knowledge Base content and identify information relevant to patient enquiries. | Generative AI Team | Knowledge Base understanding
5.2 | Generative AI Workstream | Define AI Assistant Scope | Define permitted enquiry areas and establish boundaries for AI responses. | Generative AI Team | GenAI scope definition
5.3 | Generative AI Workstream | Design Response Approach | Develop an initial approach for responding to repetitive enquiries using approved Knowledge Base information. | Generative AI Team | Response approach
5.4 | Generative AI Workstream | Validate Scope Compliance | Check that proposed responses remain within the approved Knowledge Base and do not invent clinic or medical information. | Generative AI Team | Scope compliance check
5.5 | Generative AI Workstream | Document Findings | Document the proposed approach, limitations, and observations. | Generative AI Team | GenAI summary
6.0 | Integration & Coordination | Integration & Coordination | Coordinate outputs across workstreams and maintain alignment with the central project objective. | Project Manager / Workstream Leads | Coordinated project outputs
6.1 | Integration & Coordination | Coordinate Workstreams | Track progress and dependencies across Project Management, Data Analysis, Machine Learning, and Generative AI workstreams. | Project Manager | Workstream alignment
6.2 | Integration & Coordination | Review Cross-Workstream Dependencies | Identify where outputs from one workstream are required by another. | Project Manager / Workstream Leads | Dependency updates
6.3 | Integration & Coordination | Consolidate Key Findings | Bring together relevant findings from the project workstreams. | Project Manager / Workstream Leads | Consolidated findings
7.0 | Reporting & Close-out | Reporting & Close-out | Prepare and organise project documentation and outputs. | Project Manager / Project Team | Final project documentation
7.1 | Reporting & Close-out | Prepare Project Documentation | Compile required project documents, findings, and planning outputs. | Project Manager | Project documentation package
7.2 | Reporting & Close-out | Review Deliverables | Review project outputs for completeness, consistency, and alignment with project requirements. | Project Manager / Project Team | Reviewed deliverables
7.3 | Reporting & Close-out | Document Recommendations and Next Steps | Summarise relevant findings, limitations, and potential next steps. | Project Team | Recommendations / next steps

## WBS Notes
Work Breakdown Structure (WBS) Notes
Purpose | The WBS provides a hierarchical breakdown of the broader HealthConnect project into major phases, workstreams, activities, and work packages. It is used as a planning and coordination tool.
Numbering Logic | Major phases use whole-number levels such as 1.0, 2.0 and 3.0. Activities within each phase use sub-level numbers such as 1.1, 1.2 and 2.1.
Project Management Focus | Although the WBS shows the broader project structure and major workstreams, the Project Management track is responsible for establishing and coordinating this structure rather than performing all technical tasks.